## Program Organiser Check list
| Check list | Description | Organizing team Structure
Before the Class | - A/V & session coordinators fixed | Previous monday of IE week | - IE Organizer(s)
| - Set up date/time fixed | Before sending Vol form | - Registration POC
| - Org group formed & POcs are clear | By prev Monday of IE week | - Promotion POC
| - Org Team meeting happened | Atleast on Prev Fri of the IE week | - Callling POC
| - Vol group formed | Atleast by prev Wed of the IE week | - Class/Session coordinators
| - Materials sorting done & Transport planned | By Prev sat of the IE week | - Vol coordinator(s)
| - Ishangas details recieved,stay & transport planned | By Prev sat of the IE week | - Ishanga hosting/Transport POC
| - Materials not in stock is bought | By Prev sat of the IE week | - Materials Sorting POC
| - A/V & class coordinator orientation | By Prev sat of the IE week | - Materials transport POC
| - Class vols /Reg vols orientation | By Prev Sun of the IE week | - Treasurer
- Kitchen POC
Wed - Fri Sessions | Initation Map : Display | Thrusday : QR code & Map | - Post Nurturing POC
| PCS date & time | Thursday
| Vol meet coordinator identified | Thrusday
| Announcement sheet filled | Friday
| Isha Life counter - Confirmed | Friday
Initiation set up- Saturday | Materials arrival before announced set up time | Initiation materials,Materials from other centers,Kitchen materials,Tent house materials, Vegetables ,grossories,Cleaning & Toiletries , Flowers for dias deco
Hall /Kitchen cleaning
| Hall set up | Carpets,Back drop,Triangular Banner,Dias,Sadhguru photo(Big),A/V, Window covers,Signages
| Kitchen setup | Veg cleaning,vessels cleaning,Banana leaves wiping
| Toilet readiness | Gents & Ladies - washed,dust bin/hand wash/wipes kept,Signages placed
| Water points | With drip bowl & tumblers on a plate
Dias Set up & decoration
| Chair cleaning | cleaned & counted
| Offering tables | Covered and with table signages
Name Tag table
Chappal & participant's luggage space identified
Teacher's chair & Vajrasana cloth
| Guru pooja and offering setup | on the left side of Dias
Clarity about the BSP/Vol/SSB counter set up & Materials /standees /Posters kept ready
Hall Key arrangement for morning
Initiation - Sunday | Guru Puja set up done | by 6:30:00 AM
| Kitchen/Cleaning materials are kept outside class | by 6:15 AM
| Vajrasana cloth placed | by 6:30:00 AM
| Washrooms checked, doormats,chappals placed | by 6:30 AM
| Offering vols, Parking vols, Name tag vol, inside class vol in position | by 6:30 AM
| Footwear vol in position | by 6:30 AM
| Guru Puja flower basket kept aside | by 7AM
| Ishanga & A/V vol &Class vol had BF | by 8:45am
| Vol attendance marked | by 10 AM
| Flower distribution vols oriented | by 10 AM
| Water kept during silence break | by 10 AM
| Offerings shifted during silence break | during silence break
| Coconut Prasadam preparation starts | by 11:45am
| Dining meeting conducted | by 12pm
| Serving meeting conducted | by 12pm
No movement or noise near the hall during initaition
| Photograph vol ready | by 12:30pm
| Coconut prasadam kept near dias | before afternoon session
| Guru puja offerings removed ,white cloth place below dias and washed guru pooja plate kept | before afternoon session
| BSP/Recipe sheets vols at the door | before afternoon session
| Rudraksha table set and covered | before afternoon session
| Counter set up done | by 3PM
| Cutleries kept | by 3PM
Material shifting done
Venue is as clean as we received it
send invite for second initiation on Monday in all groups
Monday- Tuesday Sessions | Announcement sheet reviewed by Ishanga | Mon
| Announcement Printouts ready | Mon Eve
| Guru Pooja set up vol identified/ done for Tues morning | Mon Eve
| Vols at counter identified | Mon, Tues

## Communications calendar
Meetings
Day of the Meeting | Attendees | Agenda
Previous Mon of the IE week | Prgm coordinator,Overall coordinator,Vol coordinator | Things to finish till Fri
Previous Fri of the IE week | Prgm coordinator,Overall coordinator,Vol coordinator,Material Transport coordinator,Material coordinator,Any other coordinator | Pending list
previous Fri or Sat of the IE week | Prgm coordinator,Overall coordinator,Vol coordinator,Class coordinators,A/V volunteer | Class & A/V responsibilities
Mon of the IE week | Prgm coordinator,Overall coordinator,Vol coordinator,Class coordinators,A/V volunteer,Class vols,Registration vols | Prep meeting,Class -Reg vol orientation,assigning the activities for 1st day
Thurs of the IE week | Prgm coordinator,Overall coordinator,Vol coordinator,Kitchen coordinator,Material Transport coordinator,Material coordinator,Any other coordinator
By Fri after Class | Prgm coordinator,Overall coordinator,Vol coordinator,Kitchen coordinator,Material Transport coordinator,Material coordinator,Class coordinator,Treasurer,Core team | Closing
Calls to the IE volunteers
Prev wed - fri of the IE week | 7 day vols | Availability,set up,orientation
Wed,Thursday | Sat,Sun vols | Fri meeting,Sat set up,Sun iniation timings & guidelines
Fri | Reminder calls- Sat set up vols | Set up timings & activity
Sat | Reminder-Sunday Pocs, offerings vol | Sun timings,team,point of contact,activity
WhatsApp msgs ( D = IE start date)
Date | Group | Message
-19D | Announcement grp,Vol groups | Vol invite
-11D | Whatsapp campaign | Vol invite
-11D | IE org group | Intro mesg
-10D | IE vol group | Intro mesg
-7D | Announcement grp,Vol groups | Vol invite
-7D | IE org group | Coordinator/Main vol list
-5D | IE org group | Class vol list
-5D | IE vol group | Set up msg
-1D morning | IE org group | 1st Day vols
-1D morning | IE vol group | Class starting msg
D+1 morning | IE vol group | Friday meeting msg
D+1 night | IE vol group | Reminder - Friday meeting
D +2 afternoon | IE vol group | Initiation set up msg
D +2 evening | IE org group | Initiation set up in charge msg
D +3 morning | IE vol group | Reminder - Initiation set up msg
D +3 , at 4pm | IE vol group, Vol groups | Initiation msg
D +3 , at 4pm | IE org group | Initiation vols in charge(hall,kitchen) & offerings msg
D +3 at 9pm | IE vol group | Initiation msg - reminder
D+4 evening | IE vol group,Vol group | Monday Guided shambhavi msg
D+6 evening | IE vol group,Vol group | Guru puja and last day msg
D+ 8 | IE vol group | Closing msg
By friday | IE org group | Closing msg

## Material Shifting Check list
IE Class Set up
From Regular Satsang venue
Carpets | FALSE
Gada Cloths | FALSE
A/V bag | FALSE
Speakers | FALSE
Projector | FALSE
Projector Screen | FALSE
Set up bag | FALSE
Set up Whites Box | FALSE
Sadhguru Chair | FALSE
Sadhguru Photo | FALSE
Water dispenser & tumblers | FALSE
From IE Materials Location
IE set up Box | FALSE
Triangular Banner | FALSE
Table set up whites | FALSE
Handouts & Registration Box | FALSE
Sanitory Box | FALSE
Cleaning Set
Broom (2) | FALSE
Mop(2) | FALSE
Buckets & mug(2) | FALSE
Dust bin (1) | FALSE
Toilet dust bin 1 | FALSE
Toilet Chappals - 2 sets | FALSE
Garbage Bag | FALSE

## Materials Check list
25 Jun IE
Handouts & Registration box
Handouts
Patanjali brochure | FALSE
Invocation | FALSE
Recipe sheet | FALSE
BSP brochure | FALSE
Practice review sheet | FALSE
Completion form | FALSE
Registration items
Nametags | FALSE
Pouches | FALSE
Safety Pins | FALSE
Attendance register | FALSE
Registration forms ( in a transparent folder) | FALSE
A4 Size sheets (min 50) | FALSE
Pens (min 50) | FALSE
Pencils (min 4) | FALSE
Sharpner 1 | FALSE
Eraser 2 | FALSE
Markers (4 different colours) + black | FALSE
Whitener 1 | FALSE
4 folders and a Big paper cover | FALSE
Set up Bag
Pooja box | FALSE
Lamp | FALSE
Chimney | FALSE
Edible Sesame Oil (atleast 500ml) | FALSE
Wicks | FALSE
Incense Stands (4) | FALSE
Agarbatti (min 30 nos) | FALSE
Match box | FALSE
Tweezer | FALSE
White tissues | FALSE
Small tray | FALSE
Soap & scrub | FALSE
Sadhguru Whites Box
Chair cloth (labeled) | FALSE
Padam cloth (Labeled) | FALSE
Deepam cloth (Labeled) | FALSE
Vajrasana cloth (Labeled) | FALSE
Chair set up rope/cloth | FALSE
Photo support cloth | FALSE
Signages Bag
(Sign) Ladies toilet | FALSE
(Sign) Gents toilet | FALSE
(Sign) Foot wear | FALSE
(Sign) Please switch off the phone | FALSE
Stationery box
Safety pin box | FALSE
Rubber bands | FALSE
Ball pin box | FALSE
Scissors | FALSE
Thread | FALSE
Gum tapes | FALSE
Stapler | FALSE
Stapler pins | FALSE
Cello tape | FALSE
Measuring tape | FALSE
Scale | FALSE
All Out | FALSE
Mosquito coil | FALSE
Herbal repellent sticks | FALSE
Paper Bits | FALSE
Folders (2) | FALSE
A4 size white papers- min (100) | FALSE
Tumblers (2) with lids | FALSE
Baskets (2) | FALSE
Attendance register- Volunteers | FALSE
Pen Box ( min 20 good pens + 2 markers + 2 pencils) | FALSE
Medical Kit
Band Aid | FALSE
Cotton | FALSE
Dettol | FALSE
Glucose | FALSE
Set up Whites Box
Clean white Table wrapping cloths (min 6) | FALSE
Cleaning cloth (min 3) | FALSE
Extra whites(a bit stained is ok, 4) | FALSE
White towels (2) | FALSE
IE Set up Box | FALSE
Tumblers (2) & plate to hold | FALSE
Paper Bits atleast 100 nos | FALSE
Pen Box ( min 20 good pens + 2 markers + 2 pencils) | FALSE
Triangular Banner - ironed and kept in a sealed cover | FALSE
Baskets (6) | FALSE
Rope | FALSE
Paper Materials tray | FALSE
Table Wrapping clothes 6 | FALSE
Cleaning cloths 4 | FALSE
Extra whites(a bit stained is ok, 4) | FALSE
Sanitory Box
Handwash- Soap dispensers - 2 bottles with refill | FALSE
Lyzol - 1 | FALSE
Odonil - spray | FALSE
Paper Napkins | FALSE
Harpic -1 | FALSE
Vim liquid and Scrubs | FALSE
Cleaning cloths | FALSE
Sanitory Pads | FALSE
Cleaning Set
Broom (2) | FALSE
Mop(2) | FALSE
Buckets & mug(2) | FALSE
Dust bin (1) | FALSE
Toilet dust bin 1 | FALSE
Toilet Chappals - 2 sets | FALSE
Garbage Bag | FALSE

## Vol Form responses
Timestamp | Name | WhatsApp number | When did you complete IE (month/year)? | Availability | Would you like to support Hall setup/windup ? | Would you like to support with your car for transporting the class material on | Would you like to join for on ground promotion on 12th & 13th Apr | Would you like to support Ishanga's stay? | Would you like to join for on ground promotion on 12th & 13th Apr | Would you like to support Ishanga's stay? | Call feedback | Calling remarks | Role | First time | Next Step
2025-02-25 05:45 | Niharika | 7411243679 | May 2021 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) |  |  |  | Yes
2025-03-01 12:21 | Niharika | 7411243679 | May 21 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) | 9th Mar, Sunday 2pm (At St. Joseph group of institutions), 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions and setup at incture technologies), 16th Mar, Sun 5pm (Windup at Incture technologies and setup at St. Joseph group of institutions), 18th Mar, Tue 9pm ( At St. Joseph group of institutions) | 9th Mar, 1pm, 15th Mar, 9pm, 16th Mar, 5pm, 18th Mar, 9pm |  | Yes
2025-03-01 16:44 | Richu Sara Shibu | 9739317450 | 2017 July | All 7 days | 9th Mar, Sunday 2pm (At St. Joseph group of institutions), 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies ) |  |  | No | [5 empty] | Yes | Calling, Kitchen Vol
2025-03-01 16:59 | Pravallika | 8074052996 | Jan 2024 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) | 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions) |  |  | No
2025-03-01 17:18 | Poonam Deswal | 9900248873 | August 2022 | Only on initiation day (15th Mar, Sunday) |  |  |  | No
2025-03-01 17:18 | Yogesh | 9845743724 | 2014 | Only on initiation day (15th Mar, Sunday) |  |  |  | No
2025-03-01 21:56 | Tushar Anand Sisodia | 9911006922 | 04/24 | All 7 days | 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies ), 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions), 18th Mar, Tue 9pm ( At St. Joseph group of institutions)
2025-03-02 01:38 | Amrutha s | 9110454813 | Oct 2024 | All 7 days |  |  |  | No
2025-03-02 02:02 | Vaidyanath ojha | 8553236564 | 08/2022 | All 7 days | 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions) |  |  | No
2025-03-02 02:09 | Sruthi | 9902179355 | March 2017 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday)
2025-03-02 02:16 | Mamatha Hegde | 9960113836 | April 2021 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) |  |  |  | No
2025-03-02 02:34 | Naveen Kumar H | 8088845709 | April, 2024 | Only on initiation day (15th Mar, Sunday)
2025-03-02 02:48 | Mahima | 9741574193 | Oct 2016 | All 7 days |  |  |  | No | [5 empty] | Yes | Class vol, Kitchen coordination
2025-03-03 15:03 | Nitesh | 9386329656 | 03/2023 | All 7 days | 9th Mar, Sunday 2pm (At St. Joseph group of institutions), 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies )
2025-03-05 12:44 | Shubhashreebj | 9449304544 | December 2024 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) | 9th Mar, Sunday 2pm (At St. Joseph group of institutions), 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies ), 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions) | No I don't have cat |  | Yes
2025-03-06 07:31 | Akansha | 7976351175 | August/2023 | All 7 days
2025-03-06 08:33 | Deepa | 9986734637 | Feb 2023 | Only on initiation day (15th Mar, Sunday)
2025-03-07 04:36 | Sakshi Pandey | 7705995160 | October 2022 | All 7 days | 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions) | Help with volunteering work |  | No
2025-03-08 03:32 | Sendhil | 9738142144 | 2020 | All 7 days | 18th Mar, Tue 9pm ( At St. Joseph group of institutions)
2025-03-08 04:23 | Subapriya | 9902023823 | Nov 2010 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) | 9th Mar, Sunday 2pm (At St. Joseph group of institutions), 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions)
2025-03-08 05:28 | Namitha K | 9986512151 | 20 | Only on initiation day (15th Mar, Sunday) | 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions)
2025-03-08 12:29 | Srividhya | 9900236551 | Feb 2025 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) |  | 15th Mar, 9pm |  | No
2025-03-08 18:00 | Amrutha | 9110454183 | Oct 2024 | All 7 days
2025-03-09 16:59 | Prashant kumar | 9899660170 | Dec/2018 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday)
2025-03-10 04:28 | Devika D Shetty | 8073911970 | October 2022 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) | 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies ), 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions) | Nil |  | Yes
2025-03-10 07:47 | Debasish Das | 9620443332 | July 2022 | Only on initiation day (15th Mar, Sunday) | 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies ) | 15th Mar, 9pm |  | No
2025-03-10 14:43 | Somasundharam | 9632034579 | 2011 | All 7 days | 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions) |  |  | No
2025-03-10 16:49 | Lakshmi | 9620346730 | 08/2025 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) | 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions)
2025-03-11 03:01 | Shiva Teja | 9885032117 | 2022 | Only on initiation day (15th Mar, Sunday) | 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions)
2025-03-11 03:04 | Sreevidya | 7795211475 | Oct 2024 | Only on initiation day (15th Mar, Sunday) | 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions) |  |  | No
2025-03-11 08:14 | Prems Pawar | 8123133382 | One year | Only on weekdays |  | 16th Mar, 5pm, 18th Mar, 9pm,
2025-03-11 09:43 | Rahi C | 8100109123 | 09/03/2025 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) | 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies ), 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions)
2025-03-11 12:48 | Prabhat | 6363550184 | January 2022 | All 7 days | 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies ), 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions), 18th Mar, Tue 9pm ( At St. Joseph group of institutions) |  |  | No
2025-03-11 17:08 | Parveen N | 9600317072 | July/2024 | All 7 days
2025-03-12 12:50 | Parvatha | 9384936255 | Oct /2024 | Only on weekdays
2025-03-14 08:42 | Thiruvengadam | 9742539163 | Oct 2014 | Initiation preparation (14th Mar, Saturday) and Initiation (15th Mar, Sunday) | 15th Mar, Sat 9pm (Windup at St. Joseph group of institutions & Set up at Incture technologies ), 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions) |  |  | Yes
2025-03-14 10:16 | Sudheer | 9880481111 | 06/2023 | Only on initiation day (15th Mar, Sunday) | 9th Mar, Sunday 2pm (At St. Joseph group of institutions) |  |  | No
2025-03-14 10:58 | Ashok E | 9591079498 | April 2024 | All 7 days | 9th Mar, Sunday 2pm (At St. Joseph group of institutions), 16th Mar, Sun 5pm (Windup at Incture technologies & Setup at St. Joseph group of institutions), 18th Mar, Tue 9pm ( At St. Joseph group of institutions) |  |  | No
2025-04-06 15:24 | Niharika | 7411243679 | May 2021 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) |  |  |  | Yes
Timestamp | Name | WhatsApp number | Role | First time | When did you complete IE (month/year)? | Availability | Would you like to support Hall setup/windup ? | Would you like to support with your car for transporting the class material on
2025-04-06 15:26 | Niharika | 7411243679 | Kitchen coordinator |  | May 2021 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) |  |  |  | Yes | Saturday setup, Initiation |  | Kitchen coordinator
2025-04-07 11:58 | Sumithra P | 7411044671 | Class volunteer | Yes | May 2015 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | Yes | No |  |  | Class volunteer | Yes | PPT support,Set up, IE
2025-04-07 12:08 | Srikanth | 7795464716 | A |  | April/2017 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy) |  | No | No |  |  | A
2025-04-07 12:21 | Dakshinamoorthy Lakshmanan | 7507099009 | A |  | 10/10 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 26th Apr, Sat 9am, 27th Apr, Sun 5pm | No | Yes | "Out of station, not availble all 7 days" |  | A
2025-04-07 12:30 | Karthikeyan | 9538798781 | A |  | October 2021 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) |  |  |  | Yes | Saturday setup, Initiation, Friday Meeting |  | A
2025-04-07 14:12 | Mamta Kumari | 8294885592 | A |  | March 2025 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No |  | Not answering | A
2025-04-07 14:57 | Yogesh Bandaru | 9845743724 | D |  | 2014 | Only on initiation day (27th Apr, Sunday) |  |  |  |  | Initiation |  | D
2025-04-07 15:21 | Priyanka Soni | 9685167055 | Class volunteer,Initiation | Yes | Aug 2024 | All 7 days | [6 empty] | Class volunteer,Initiation | Yes | Class vol, Set up
2025-04-12 14:22 | Rohan M S | 8123676861 | Sat Set up ,Initiation | Yes | June/2022 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) | [5 empty] | Sat Set up ,Initiation | Yes | PPT support,Set up, IE
2025-04-13 09:39 | Mahima S | 9741574193 | Class volunteer,kitchen coordinatior |  | Aug 2016 | All 7 days |  | 26th Apr, Sat 9am | No | No |  |  | Class volunteer,kitchen coordinatior
2025-04-13 09:50 | Yogesh Bandaru | 9845743724 | Initation,Sat set up |  | 2014 | Only on initiation day (27th Apr, Sunday) |  |  |  |  | Duplicate |  | Initation,Sat set up
2025-04-13 09:55 | Mandeep Kalra | 7795593093 | Material coordination |  | Dec/2017 | Only on weekdays |  | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  |  |  |  | Material coordination
2025-04-13 11:39 | Manjari sinha | 8599861160 | Initiation | Yes | 2024 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No | Initiation |  | Initiation | Yes
2025-04-13 13:14 | Nagesh verma | 8871295949 | A |  | Aug/2023 | All 7 days | 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No |  |  | A
2025-04-13 13:32 | Kumari kumkum | 8210888686 | A |  | 2024 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  | Yes | Saturday setup, Initiation |  | A
2025-04-14 04:59 | Murali ravi | 9019265694 | A |  | March/2025 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy) | [5 empty] | A
2025-04-14 08:44 | Manan Patel | 9879882048 | Class volunteer ,sat set up, initiation |  | December 2018 | All 7 days | 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | [5 empty] | Class volunteer ,sat set up, initiation
2025-04-17 06:58 | Kunal | 7991128920 | A |  | 05/2023 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy) | [5 empty] | A
2025-04-17 07:20 | Gopinath T S | 7483370789 | A/V volunteer |  | April 2022 | All 7 days | 26th Apr, Sat 9am (Transform Cricket Academy) |  |  | Yes |  |  | A/V volunteer
2025-04-17 07:27 | Binoy | 7044090701 | Material transport,Initiation |  | July 2023 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  |  | Saturday setup, Initiation |  | Material transport,Initiation
2025-04-17 11:23 | Sudheer | 9880481111 | Initiation kitchen cleaning coordinator |  | June 2023 | Only on initiation day (27th Apr, Sunday) | 20th Apr, Sunday 2pm (Transform Cricket Academy) |  | No | No | Initiation | tentative on 26th | Initiation kitchen cleaning coordinator
2025-04-17 13:43 | Ojasvini Singh | 7996086105 | A |  | 2024 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | Yes | Yes |  |  | A
2025-04-18 15:43 | Praveen Acharya | 9880032253 | Class coordinator |  | 2022 August | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | Yes |  |  |  | Class coordinator
2025-04-20 23:06 | Prasanna babu S | 9003280158 | Class volunteer | Yes | April 2015 | All 7 days |  |  | No | No |  |  | Class volunteer | Yes | PPT support,Set up
2025-04-21 11:30 | Rajath MB | 8105229838 | A |  | 2018 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) |  | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  |  | Friday Meeting, Saturday setup, Initiation | Anna is willing to support Transport on 26th and 27th. | A
2025-04-21 14:16 | Jagadish Kumar | 9900919013 | Initiation |  | June 2018 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | No | No |  |  | Initiation
2025-04-21 16:12 | Rajath MB | 8105229838 | A |  | 2018 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  |  | Duplicate | Duplicate | A
2025-04-21 16:15 | Madhavi | 9986644148 | Initaition |  | June/2011 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No | Initiation | 27th she will come. working so not possible for anyother days. | Initaition
2025-04-21 18:36 | Harshavardhan | 9880153642 | A |  | 02/2019 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 27th Apr, Sun 5pm | No | Yes | Initiation | 27th morning he can be there. Travelling from tomorrow so not available for anyother days. He has a duster car. He can offer for material shifting | Material Transport to BG | Yes
2025-04-21 18:36 | Manjari | 8599861160 | Initiation | Yes | May/2024 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No | Initiation | She is available on 27th morning. 26th tentative. working so Friday is not possible. | Initiation | Yes
2025-04-22 11:39 | Vivek N | 9986626700 | A |  | 2022 | All 7 days | 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | Yes | Yes |  |  | A
2025-04-22 19:08 | Suresh | 9108063672 | A |  | Feb | All 7 days | 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | No | No |  |  | A
2025-04-22 20:53 | Ritu Agrawal | 7500626269 | A |  | 04/2025 | Only on weekdays | 26th Apr, Sat 9am (Transform Cricket Academy) | [5 empty] | A
2025-04-23 13:45 | Ramesh C | 8105625098 | Initaition | Yes | 2023 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  |  |  | Initiation | He will come within 6 am. Came for earlier class also. | Initaition | Yes
2025-04-23 18:25 | Bharathi vankadari | 9611188455 | A |  | 6/2021 | Only on initiation day (27th Apr, Sunday) | [6 empty] | A
2025-04-24 05:02 | Smitha | 9632755331 | Initaition | Yes | July, 2021 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | [6 empty] | Initaition | Yes
2025-04-26 08:33 | Bhaavya C | 9550878762 | Initiation |  | March 2025 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 26th Apr, Sat 9am (Transform Cricket Academy) | 26th Apr, Sat 9am |  |  |  |  | Initiation
2025-04-26 08:33 | Suhrut |  | Program coordinator | [9 empty] | Program coordinator
2025-04-26 08:33 | Manasa |  | Initation Kitchen coordinator | [9 empty] | Initation Kitchen coordinator
2025-04-26 08:33 | Pranavi |  | Initation Kitchen coordinator | [9 empty] | Initation Kitchen coordinator
2025-04-26 08:33 | Tushar |  | Overall coordinator | [9 empty] | Overall coordinator
2025-04-26 08:33 | Bhavani |  | Initation Kitchen coordinator | [9 empty] | Initation Kitchen coordinator
2025-04-26 08:33 | Bini |  | Initation Kitchen coordinator | [9 empty] | Initation Kitchen coordinator
2025-04-26 08:33 | Sarusha |  | Initation Kitchen coordinator | [9 empty] | Initation Kitchen coordinator
2025-04-26 08:33 | Jagadish |  | Initation | [9 empty] | Initation
2025-04-26 08:33 | Kumarvel |  | Initation | [9 empty] | Initation
2025-04-26 08:33 | Sendhil |  | Hall team | [9 empty] | Hall team
2025-04-24 05:02 | Uma | 6360779176 | Initiation | [9 empty] | Initiation | Yes | Save Soil
2025-04-24 05:02 | Uma Devi | 9483573011 | Initiation | Yes | [8 empty] | Initiation | Yes

## Initiation volunteers
IE Program Date | 2025-04-01 | 2025-06-01
Saturday
IE coordinator | Tushar
Transport - In charge | Mandeep
IE class material after morning class/After initiation | Mandeep,Mandeep
IE class materials after evening class/After initiation | NA
Materials from other centers on before Sat setup/after Initiation | Binoy,Harshavardhan
Center Initiation materials from storage/after initiation | Sendhil
Kitchen materials before Sat setup / After initiation | Bini,Bini
Kitchen Grocery/Vegetables/Isha products
Tent house before Sat setup / After initiation | Sendhil,Sendhil
Material list - Overall in charge
Kitchen material shifting | Bini | Bini
Initiation material shifting | Manjula/Sendhil | Manjula/Sendhil
Sat morning class material | Praveen | N/A
Saturday night Class materials | NA | N/A
Other center materials | Mandeep | N/A
Sat Set up Coordinators - Overall | Suhrut | Praveen
Hall set up -afternoon | Tushar,Praveen,Sendhil,Binoy,Priyanka,Rohan | Tushar - Sendhil, others
Kitchen set up | Pranavi/Niharika | Pranavi/Manasa (15 vol)
Dias | Radharanjan,Sendhil | Sendhil (Jagadish,Shashi)
Toilets & Hygiene | Priyanka,Manan | Santosh, Ladies toilet?
Flower Decoration | Manasa,Sumitra,Manan,Bini | Smitha,Amruta,Bhaya
Night setup | NA
Sunday
Hall -Outside Coordinator | Tushar
Hall Team (Offering Shifting, Chair set up, Silence break, Dining set up) | Praveen
Guru puja setup | Smitha 9632755331 | Santosh
Dias/Flowers | Manasa / Sumitra 7411044671 | Bhavya,Smita
Ishanagas | Niharika,Shruti sharma | To find (Anju)
Offering collection /shifting | Hall team + Smitha 7411044671, if req Binoy anna | Sudheer,Shashi,Vikas,Santosh + Tushar/nitesh/Sendhil
Tags & Latecomers &Attendance | Priyanka 9685167055 | Bhavya
Toilets & Hygiene | Priyanka | Santosh, one akka
A/V | Gopinath | Arnav
Inside class coordinator | Praveen | Jagadish
Outside class coordinator | Tushar | Check with Nitesh
Dining coordinator | Suhrut | Jayakumar
BSP/Recipe sheets | Sumitra/Priyanka soni | Smitha/Bhavya- Amruta akka to guide
Coconut Prasadam | Kumarvel | Tiruvenkdam,Kumarvel
Isha life counter | Kumarvel | Santosh,Kumarvel
Rudrakhsa table set up | Jagadish kumar (9900919013) | Mamta
Counters | Binoy | Shashi,Vikas- Sudheer anna to guide
Class set up
Wind up | Mandeep
Kitchen - Overall | Bhavani | Bini
Vegetable cutting in charge | Sarusha | Pranavi
Kanji | Kumarvel | Kumarvel,Santosh | Niharika
Mixing in charge | Niharika | Manasa
Silence - water | Kumarvel | Kumarvel,Santosh
Serving meet | Madhav/Bhavani | Bini
Dining meet | Suhrut | Nitesh
Serving in charge | Madhav/Bhavani | Manasa ( Bini akka to guide)
Cleaning & Organising | Bini | Manjula, Bhavya | Niharika
Materials & Windup | Bini | Manjula, Bhavya | Niharika
Offerings/Volunteers - Overall | Bini
Guru Puja Offerings | Smitha | Santosh
Lemon/Potato/Garlic | Bini | Tushar
Flowers for decoration | Manan,Sumitra | Bhavya & Smita
Photograph | Mohit | Nitesh
Groundnut |  | Santosh
Sprouted green gram |  | Vikas
Pulikachil | Bhavya | Uma
Talidam |  | Bhavya
Coconut breaking tool | Mahima | Shashi
Coconut grater | Praveen | Manjula
Honey | Bini | Poonam

## Latest Form Responses
Timestamp | Name | WhatsApp number | Role | First time | When did you complete IE (month/year)? | Availability | Would you like to support Hall setup/windup ? | Would you like to support with your car for transporting the class material on | Would you like to join for on ground promotion on 12th & 13th Apr | Would you like to support Ishanga's stay? | Call feedback | Calling remarks
2025-04-06 15:26 | Niharika | 7411243679 | Kitchen coordinator |  | May 2021 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) |  |  |  | Yes | Saturday setup, Initiation |  | - Invite for Friday meet (Plan & also prepare ourselves fro initiation) - Sat setup - setting ambience for initiation - Sunday by 6:30am - max support req between 6:30 -8:30am
2025-04-07 11:58 | Sumithra P | 7411044671 | Class volunteer | Yes | May 2015 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | Yes | No
2025-04-07 12:08 | Srikanth | 7795464716 | A |  | April/2017 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy) |  | No | No
2025-04-07 12:21 | Dakshinamoorthy Lakshmanan | 7507099009 | A |  | 10/10 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 26th Apr, Sat 9am, 27th Apr, Sun 5pm | No | Yes | "Out of station, not availble all 7 days" |  | Fix vol for dias and flower arrgmnt Identify material shifting in charges Hall team Kitchen team - Ganji & sub coordinators Serving meet & serving in charge
2025-04-07 12:30 | Karthikeyan | 9538798781 | A |  | October 2021 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) |  |  |  | Yes | Saturday setup, Initiation, Friday Meeting
2025-04-07 14:12 | Mamta Kumari | 8294885592 | A |  | March 2025 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No |  | Not answering | Windup vols
2025-04-07 14:57 | Yogesh Bandaru | 9845743724 | D |  | 2014 | Only on initiation day (27th Apr, Sunday) |  |  |  |  | Initiation
2025-04-07 15:21 | Priyanka Soni | 9685167055 | Class volunteer,Initiation | Yes | Aug 2024 | All 7 days
2025-04-12 14:22 | Rohan M S | 8123676861 | Sat Set up ,Initiation | Yes | June/2022 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy)
2025-04-13 09:39 | Mahima S | 9741574193 | Class volunteer,kitchen coordinatior |  | Aug 2016 | All 7 days |  | 26th Apr, Sat 9am | No | No
2025-04-13 09:50 | Yogesh Bandaru | 9845743724 | Initation,Sat set up |  | 2014 | Only on initiation day (27th Apr, Sunday) |  |  |  |  | Duplicate
2025-04-13 09:55 | Mandeep Kalra | 7795593093 | Material coordination |  | Dec/2017 | Only on weekdays |  | 26th Apr, Sat 9am, 27th Apr, Sun 5pm
2025-04-13 11:39 | Manjari sinha | 8599861160 | Initiation | Yes | 2024 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No | Initiation
2025-04-13 13:14 | Nagesh verma | 8871295949 | A |  | Aug/2023 | All 7 days | 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No
2025-04-13 13:32 | Kumari kumkum | 8210888686 | A |  | 2024 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  | Yes | Saturday setup, Initiation
2025-04-14 04:59 | Murali ravi | 9019265694 | A |  | March/2025 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy)
2025-04-14 08:44 | Manan Patel | 9879882048 | Class volunteer ,sat set up, initiation |  | December 2018 | All 7 days | 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy)
2025-04-17 06:58 | Kunal | 7991128920 | A |  | 05/2023 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy)
2025-04-17 06:59 | Priyanka Soni | 9685167055 | D |  | aug 2024 | All 7 days
2025-04-17 07:20 | Gopinath T S | 7483370789 | A/V volunteer |  | April 2022 | All 7 days | 26th Apr, Sat 9am (Transform Cricket Academy) |  |  | Yes
2025-04-17 07:27 | Binoy | 7044090701 | Material transport,Initiation |  | July 2023 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  |  | Saturday setup, Initiation |  | CAR
2025-04-17 11:23 | Sudheer | 9880481111 | Initiation kitchen cleaning coordinator |  | June 2023 | Only on initiation day (27th Apr, Sunday) | 20th Apr, Sunday 2pm (Transform Cricket Academy) |  | No | No | Initiation | tentative on 26th
2025-04-17 13:43 | Ojasvini Singh | 7996086105 | A |  | 2024 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | Yes | Yes
2025-04-18 15:43 | Praveen Acharya | 9880032253 | Class coordinator |  | 2022 August | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | Yes
2025-04-20 23:06 | Prasanna babu S | 9003280158 | Class volunteer | Yes | April 2015 | All 7 days |  |  | No | No
2025-04-21 11:30 | Rajath MB | 8105229838 | A |  | 2018 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) |  | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  |  | Friday Meeting, Saturday setup, Initiation | Anna is willing to support Transport on 26th and 27th. | CAR
2025-04-21 14:16 | Jagadish Kumar | 9900919013 | Initiation |  | June 2018 | All 7 days | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | No | No
2025-04-21 16:12 | Rajath MB | 8105229838 | A |  | 2018 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 20th Apr, Sunday 2pm (Transform Cricket Academy), 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 26th Apr, Sat 9am, 27th Apr, Sun 5pm |  |  | Duplicate | Duplicate
2025-04-21 16:15 | Madhavi | 9986644148 | Initaition |  | June/2011 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No | Initiation | 27th she will come. working so not possible for anyother days.
2025-04-21 18:36 | Harshavardhan | 9880153642 | A |  | 02/2019 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) | 27th Apr, Sun 5pm | No | Yes | Initiation | 27th morning he can be there. Travelling from tomorrow so not available for anyother days. He has a duster car. He can offer for material shifting | CAR
2025-04-21 18:36 | Manjari | 8599861160 | Initiation | Yes | May/2024 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No | Initiation | She is available on 27th morning. 26th tentative. working so Friday is not possible.
2025-04-21 20:28 | Manjari | 8599861160 | D |  | May/2024 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  | No | No | Duplicate | Duplicate
2025-04-22 11:39 | Vivek N | 9986626700 | A |  | 2022 | All 7 days | 26th Apr, Sat 9am (Transform Cricket Academy), 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy), 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | Yes | Yes
2025-04-22 19:08 | Suresh | 9108063672 | A |  | Feb | All 7 days | 29th Apr, Tue 9am ( At Transform Cricket Academy) |  | No | No
2025-04-22 20:53 | Ritu Agrawal | 7500626269 | A |  | 04/2025 | Only on weekdays | 26th Apr, Sat 9am (Transform Cricket Academy)
2025-04-23 13:45 | Ramesh C | 8105625098 | Initaition | Yes | 2023 | Only on initiation day (27th Apr, Sunday) | 27th Apr, Sun 5pm (Windup at Incture technologies & Setup at Transform Cricket Academy) |  |  |  | Initiation | He will come within 6 am. Came for earlier class also.
2025-04-23 18:25 | Bharathi vankadari | 9611188455 | A |  | 6/2021 | Only on initiation day (27th Apr, Sunday)
2025-04-24 05:02 | Smitha | 9632755331 | Initaition | Yes | July, 2021 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday)
2025-04-26 08:33 | Bhaavya C | 9550878762 | Initiation |  | March 2025 | Initiation preparation (26th Apr, Saturday) and Initiation (27th Apr, Sunday) | 26th Apr, Sat 9am (Transform Cricket Academy) | 26th Apr, Sat 9am
| Suhrut |  | Program coordinator
| Manasa |  | Initation Kitchen coordinator
| Pranavi |  | Initation Kitchen coordinator
| Tushar |  | Overall coordinator
| Bhavani |  | Initation Kitchen coordinator
| Bini |  | Initation Kitchen coordinator
| Sarusha |  | Initation Kitchen coordinator
| Jagadish |  | Initation
| Kumarvel |  | Initation
| Sendhil |  | Hall team
| Uma | 63607 79176 | Initiation
| Uma Devi | 9483573011 | Initiation | Yes